## Feature Roadmap
ID | Feature Name | Priority | Category | Effort | Business Value | Status | Target Quarter | Dependencies | Description | Key Requirements | Success Metrics | Notes
P0.1 | Assessment Template System | P0 | Core Assessment | L (3-4 weeks) | Critical | Not Started | Q1 | None | Implement support for multiple assessment templates (Gate 0, Gate 1, PAR, Gate 3) with template selection and criteria filtering. | Database tables for templates and criteria; Template selection UI; Criteria filtered by template; Seed data for 4 standard templates; Migration of existing projects | Users can select from 4 assessment templates; Each template shows correct number of criteria; Existing projects continue to function | Biggest P0 feature. Game-changer for product positioning.
P0.2 | Overall Project Summary Assessment | P0 | Core Assessment | M (1-2 weeks) | Critical | ✅ Complete | Q1 | None | AI-generated summary assessment that synthesizes individual criterion assessments into overall project rating with executive summary. | N8N workflow extension on done branch; AI agent reviews all assessments; Weighted scoring calculation; Database table for summaries; Summary display in UI | Every assessment produces overall summary; Summary includes all required sections; Overall rating reflects weighted scores | Completed. Provides executive-level view of assessment results.
P0.3 | Satisfaction Score UX Fix | P0 | User Experience | S (3-5 days) | High | ✅ Complete | Q1 | None | Replace confusing confidence percentage with intuitive satisfaction score showing how well each criterion is met (0-100%). | Add satisfaction_score field; Update N8N AI prompt; Update UI display; Show confidence as qualitative label; Update existing records | Users understand 90% means 90% satisfied; Reduced confusion; Clear visual distinction | Completed. Major UX improvement for result interpretation.
P0.4 | Production Webhook Configuration | P0 | Infrastructure | XS (1-2 days) | Critical | ✅ Complete | Q1 | None | Ensure all N8N workflows use production webhook URLs and are properly activated. | Update backend to use production URLs; Add webhook URLs to env variables; Verify workflows active; Test end-to-end; Document configuration | Document upload triggers embedding; Assessment triggers workflow; No test webhooks in production | Completed. Essential for production deployment.
P0.5 | Error Handling and User Feedback | P0 | User Experience | S (3-5 days) | High | Not Started | Q1 | None | Comprehensive error handling for failed workflows, network errors, and edge cases with clear user feedback. | Loading states for all operations; Error messages with actionable guidance; Retry mechanisms; Toast notifications; Error logging | No blank screens or silent failures; Clear actionable errors; 95%+ errors have recovery paths | Quick win. Significantly improves user experience.
P0.6 | Basic Database Migrations | P0 | Infrastructure | S (3-5 days) | Critical | Not Started | Q1 | None | Implement Drizzle Kit migrations to track database schema changes in version control. | Initialize Drizzle Kit; Generate initial migration; Document workflow; Add migration commands; Test rollback | All schema changes tracked; Migrations apply to fresh database; Team can safely make changes | Essential for database integrity as app evolves.
P1.1 | Multi-Document Upload Enhancement | P1 | Document Management | M (1-2 weeks) | High | Not Started | Q2 | None | Enhanced document upload supporting unlimited files, batch operations, progress tracking, and additional file types. | Remove 3-document limit; Batch upload with progress bars; Document type tagging; Support DOCX/XLSX/TXT; File size validation; Drag-and-drop reordering | Users upload 10+ documents without issues; Clear progress feedback; Support common government formats | User-requested feature. Improves upload experience.
P1.2 | Document Management Features | P1 | Document Management | M (1-2 weeks) | High | Not Started | Q2 | None | Essential document management capabilities including replace, delete, download, and preview. | Replace document with history; Delete with confirmation; Download original; In-browser PDF preview; Version history display; Metadata editing | Users manage documents without leaving app; Changes tracked; No accidental data loss | Core functionality for document lifecycle management.
P1.3 | Project Dashboard | P1 | User Experience | M (1-2 weeks) | High | Not Started | Q2 | P0.2 | Dashboard showing all user projects with status, progress, and quick actions. | Card-based layout with metrics; Status indicators; Last assessment date and rating; Quick actions; Search and filter; Sort options; Empty state | Users find projects quickly; Dashboard loads <2 seconds; Clear visual hierarchy | Significantly improves navigation and project overview.
P1.4 | Assessment History and Tracking | P1 | Core Assessment | M (1-2 weeks) | High | Not Started | Q2 | None | Track multiple assessment runs over time. Show history, compare results, track improvement. | Store multiple runs per project; History timeline view; Side-by-side comparison; Track changes over time; Document inclusion tracking; Run metadata | Users see project progress over time; Easy to identify improvements; Historical data retained | Enables trend analysis and progress tracking.
P1.5 | PDF Report Export | P1 | Reporting | M (1-2 weeks) | High | Not Started | Q2 | P0.2 | Generate professional PDF reports of assessment results for stakeholder sharing. | Branded PDF template; Executive summary page; Detailed findings; Charts and visualizations; Document list appendix; Configurable sections; Download button | Professional-looking reports; Generate in <10 seconds; Suitable for executive presentation | Critical for stakeholder communication and archival.
P1.6 | Weighted Scoring Implementation | P1 | Core Assessment | M (1-2 weeks) | High | Not Started | Q2 | P0.1 | Implement weighted scoring where each criterion has percentage weight and overall score is weighted average. | Add weight field to criteria; Display weights in UI; Calculate weighted overall score; Apply thresholds for RAG; Critical criterion rule; Score breakdown by category | Overall ratings reflect criterion importance; Critical criteria flagged; Score calculation transparent | Aligns with official GMPP assessment methodology.
P1.7 | N8N Workflow Version Control | P1 | Infrastructure | S (3-5 days) | High | Not Started | Q3 | None | Export N8N workflows to JSON files in Git repository for version control and backup. | Export workflows to /n8n-workflows/; Add to Git; Document export process; Add to deployment checklist; Optional automation script | Workflows backed up in Git; Changes tracked over time; Can restore from backup | See Developer's Guide for implementation steps.
P1.8 | Basic Automated Testing | P1 | Infrastructure | M (1-2 weeks) | High | Not Started | Q3 | None | Add automated tests for critical functionality to catch regressions early. | Set up Vitest; Unit tests for database helpers; Unit tests for tRPC procedures; Integration tests for key flows; Test fixtures; CI/CD integration | 50%+ code coverage on critical paths; Tests run in <30 seconds; Catches common bugs | See Developer's Guide for setup instructions.
P1.9 | User Guide and Documentation | P1 | User Experience | S (3-5 days) | Medium | Not Started | Q3 | P0.1, P0.2 | Comprehensive user guide explaining how to use the application and interpret results. | Getting started guide; How to create projects and upload documents; Understanding results; Interpreting RAG ratings; Best practices; FAQ; Embedded help tooltips | Reduced support requests; Users self-serve for common questions; Clear onboarding | Reduces support burden and improves user adoption.
P1.10 | Assessment Criteria Customization | P1 | Core Assessment | L (3-4 weeks) | Medium | Not Started | Q3 | P0.1 | Allow users to customize assessment criteria within template or create custom templates. | Clone existing template; Add/remove/edit criteria; Adjust weights; Save as custom template; Share templates (admin only); Template versioning | Users tailor assessments to needs; Custom templates don't break functionality; Template library grows | Enables organization-specific assessment frameworks.
P2.1 | Collaborative Features | P2 | Collaboration | L (3-4 weeks) | Medium | Not Started | Q4 | None | Enable multiple users to collaborate on projects with comments, mentions, and activity tracking. | Add users to projects with roles; Comments on assessments; @mentions with notifications; Activity feed; Email notifications; Resolve/unresolve comments | Teams collaborate on assessments; Reduced email back-and-forth; Clear audit trail | Transforms from individual to team tool.
P2.2 | Assessment Comparison and Benchmarking | P2 | Analytics | M (1-2 weeks) | Medium | Not Started | Q4 | P1.4 | Compare projects against each other or benchmarks to identify patterns and best practices. | Compare 2-3 projects side-by-side; Benchmark against portfolio average; Identify common failure patterns; Best-in-class comparison; Anonymized benchmarking; Export comparison reports | Users gain insights from cross-project analysis; Identify systemic issues; Learn from successful projects | Enables portfolio-level insights and learning.
P2.3 | Advanced Document Processing | P2 | Document Management | L (3-4 weeks) | Medium | Not Started | Q4 | None | Enhanced document processing including OCR, table extraction, and structured data extraction. | OCR for scanned documents; Table extraction and parsing; Extract key data points; Document classification; Multi-language support; Improved chunking strategies | Handle scanned/image PDFs; Extract structured data from tables; Improved assessment accuracy | Handles wider variety of document formats and quality.
P2.4 | Interactive Assessment Workflow | P2 | Core Assessment | L (3-4 weeks) | Medium | Not Started | Q4 | None | Allow users to guide assessment process, provide context, and refine results interactively. | Wizard-style setup; User provides context per criterion; Pause/resume assessment; Override AI ratings with justification; Request re-assessment; Provide additional documents mid-assessment | Users feel in control; More accurate results through human guidance; Reduced manual corrections | Hybrid human-AI assessment approach.
P2.5 | Advanced Visualizations and Analytics | P2 | Analytics | M (1-2 weeks) | Medium | Not Started | Q4 | P1.4 | Rich visualizations of assessment data including charts, heatmaps, and trend analysis. | RAG distribution pie chart; Scores by category radar chart; Trend lines over time; Heatmap of criteria performance; Portfolio-level analytics; Export charts; Interactive drill-down | Users quickly understand results; Visual insights drive action; Executive-friendly presentations | Makes data more accessible and actionable.
P2.6 | Email Notifications and Alerts | P2 | User Experience | S (3-5 days) | Medium | Not Started | Q4 | None | Automated email notifications for key events and configurable alerts. | Assessment complete notification; Critical issues alert; Weekly digest; Reminder for overdue assessments; Customizable preferences; Branded email templates | Users stay informed without checking app constantly; Timely action on critical issues; Reduced missed deadlines | Keeps users engaged and informed proactively.
P2.7 | Mobile-Responsive Design | P2 | User Experience | M (1-2 weeks) | Medium | Not Started | Q4 | None | Optimize UI for mobile and tablet devices for on-the-go access. | Responsive layouts for all pages; Touch-friendly interactions; Mobile-optimized upload; Simplified mobile navigation; PWA support; Offline viewing of cached results | Usable on phones and tablets; No horizontal scrolling; Fast load on mobile networks | Expands accessibility for field users.
P2.8 | Integration with Project Management Tools | P2 | Integration | M (1-2 weeks) | Medium | Not Started | Q4 | None | Integrate with common PM tools to sync project data and assessment results. | Microsoft Project integration; Jira integration; Export to Excel/CSV; API webhooks; Zapier integration; Automated sync of metadata | Reduced manual data entry; Assessment results flow to PM tools; Single source of truth | Reduces friction in existing workflows.
P2.9 | Audit Trail and Compliance | P2 | Governance | M (1-2 weeks) | Medium | Not Started | Y2 | None | Comprehensive audit logging for compliance with government record-keeping requirements. | Log all user actions; Track document access; Record assessment runs; Export audit logs; Retention policy configuration; Immutable audit records | Full audit trail for compliance; Can answer who/what/when; Meets government audit requirements | Essential for regulated environments.
P2.10 | Bulk Operations and Batch Processing | P2 | User Experience | M (1-2 weeks) | Low | Not Started | Y2 | None | Perform operations on multiple projects or documents at once. | Multi-select projects; Bulk delete; Bulk export; Batch assessment runs; Bulk document upload across projects; Progress tracking | Efficient management of large portfolios; Time savings for power users; No performance degradation | Scales to portfolio management use cases.
P3.1 | AI Assistant Chat Interface | P3 | AI Features | L (3-4 weeks) | Low | Not Started | Y2 | None | Conversational AI assistant that answers questions about assessments and provides guidance. | Chat interface in project page; Ask questions about criteria; Request clarification on findings; Get improvement recommendations; Context-aware responses; Chat history persistence | Users get instant answers; Reduced external support; Improved understanding of results | Advanced AI feature for future consideration.
P3.2 | Automated Recommendations Engine | P3 | AI Features | XL (1-2 months) | Low | Not Started | Y2 | P1.4 | ML system that learns from historical assessments to provide personalized recommendations. | Train models on history; Predict likely issues; Suggest proactive mitigations; Recommend similar successful projects; Continuous learning; Explainable AI | Recommendations are accurate and actionable; Users adopt recommendations; Measurable improvement in outcomes | Requires significant data volume and ML expertise.
P3.3 | Advanced Search and Filtering | P3 | User Experience | M (1-2 weeks) | Low | Not Started | Y2 | None | Powerful search across all projects, documents, and assessments with advanced filters. | Full-text search across content; Filter by multiple dimensions; Saved searches; Search within documents; Boolean operators; Search suggestions and autocomplete | Users find information quickly; Search is fast (<1 second); High search success rate | Useful for large portfolios with many projects.
P3.4 | White-Label and Multi-Tenancy | P3 | Platform | XL (1-2 months) | Low | Not Started | Y2 | None | Support multiple organizations with separate data, branding, and configuration. | Tenant isolation; Custom branding per tenant; Tenant-specific templates; Usage tracking and billing; Tenant admin portal; Cross-tenant analytics | Can onboard new organizations quickly; Complete data isolation; Scalable to 100+ tenants | Major architectural change for SaaS model.

## Summary
Feature Roadmap Summary
Priority Level | Total Features | Completed
P0 (Critical) | 6 | 3
P1 (High Value) | 10 | 0
P2 (Medium Value) | 10 | 0
P3 (Low Priority) | 4 | 0
Total Features | 30 | 3
Progress | 3/30 | 10.0%